## ENVISION
task | task_details | role | hours
Project Initiation | Conduct a "soft launch" initial project planning call with the immediate ServiceNow stakeholders. | EM | 4
Project Pre-Work | Prepare and deliver "pre-work" materials. Pre-work may include assets comparable to the following examples: > Business Case template - Document that provides justification for the ServiceNow implementation. > Company Vision & Strategy template - Document that describes the company's strategic drivers and their vision for digital transformation. | BPC | 2

## INITIATE
task | task_details_simple | role | hours
Review and Validate "Envision Phase" Outputs | This activity aims to validate business assumptions and ensure alignment between the business owners and the implementation team. > Business Case Updated Requirements > Review of the Recommended Implementation Sequencing | BPC | 4
Project Planning | Create detailed project plan and work breakdown structure. | EM | 12
Kick-Off Meetings | Conduct kick-off meetings to align scope and objectives with project sponsor(s) and the project team. | EM | 4
Review Pre-Work Responses (BPC) | Review current customer environment and operation model. > Identify any pre-actions to be taken by Client to support the project. | BPC | 8
Review Pre-Work Responses (TA) | Review current customer environment and operation model. > Identify any pre-actions to be taken by Client to support the project. | TA | 4
Set Up Environment | Provision Instance and Activate Plugins | TC | 4
Define Change Strategy | Understand stakeholder objectives and create high level Organizational Change Management (OCM) plan (i.e., training). | BPC | 2
Scope Management | Establish a project Change Order process. | EM | 2

## DEFINE
task | task_details | role | hours
Company Setup & Configuration (workshop) | workshop | TC | 2
Connectivity Setup & Configuration (workshop) | workshop | TC | 4
Foundational Data Population, Configuration, and Remediation (workshop) | workshop | TC | 6

## DESIGN
task | task_details | role | hours
Create Development Backlog | Document and size all requirements gathered during the workshops into a concise requirements list which will be reviewed and approved prior to creating a detailed design. | BPC | 12
Load and Define Design | Transform the Development Backlog into requirement tasks within Advance's development tracker and add specific build details to the requirements selected for implementation. | TA | 16
Project Sprint Development | Organize project tasks into a collection of project sprints and stories. > Perform up to two (2) readbacks with the Client to verify project timeline, key milestones, and task alignment. > Verify resource plan and the availability Client resources when assistance or co-development efforts are required. | TA | 16

## BUILD
task | task_details | role | hours
Company Setup & Configuration | Provision Service Now instances, initial system setup, as well as plugin activation/configuration. > System Configuration > Welcome Page | TC | 4
Connectivity Setup & Configuration | Configure the ServiceNow instance to support inbound and outbound email notification. Integrate it with the Client's existing LDAP and single sign-on (SSO) solutions. > Email Properties - Setup/Configure one (1) Email Mailbox (Assuming ServiceNow Email Addresses). > LDAP Integration - Active Directory integration for user / group sync using default LDAP transform mappings supplied out of the box ("OOTB"). > Single Sign On (SSO) Integration - Configure SSO in ServiceNow to work with one (1) external tool such as Okta or ADFS. Setup/Configure one (1) Email Mailbox (Assuming ServiceNow Email Addresses) | TC | 12
Foundational Data Population, Configuration, and Remediation | Import users, groups, group members, companies, departments, and locations to provide access to the instance and facilitate automated processes, such as auto-assignment of tasks. Assign roles to groups to provide access to all group members or assign roles to individual users. > Departments > Locations > Companies > Users > Groups > Group Members > Assign Roles Advance shall load data up to two (2) times, and Client will have an opportunity to review/remediate data after the first load. | TC | 16

## TRANSITION
task | task_details | role | hours
Deploy Code to Test Environment | > Deploy Code to System Test Environment > Deploy Code to UAT Environment | QAE | 4
Test Strategy | > Conduct Testing Workshop > Document Test Strategy & Data Plan | BPC | 8
Plan User Accepted Testing | > Create User Acceptance Test Scenarios & Scripts > Build User Acceptance Test Plan > UAT Logistics and Preparation Session > Draft and Issue UAT Training Materials | BPC | 8
Plan System Testing | > Create System Test Scenarios & Scripts > Build System Test Plan | BPC | 8
Conduct User Accepted Testing | > Data Set-up for UAT > UAT Training for Testers > Execute UAT > UAT Defect Management | QAE | 8
Conduct System Testing | Data Set-up for System Test > Ensure all test data is loaded and validated in a testing instance in preparation for System Testing, so that all aspects can be tested with the correct foundational data present. > Execute System Testing > System Test Defect Management | QAE | 8
Training Preparation | Review training scope and the final content to be included in training based on the Deploy stage configurations. | BPC | 2
Create Training Materials | Create quick reference guide training materials for: > Deployed ServiceNow capabilities Training shall be provided in English. | BPC | 4
Training Sessions | Perform training sessions for: > Deployed ServiceNow capabilities Training shall be provided in English. | BPC | 8
Go-Live Transition | > Execute Cut-over Dry Run(s) > Deploy Code to Production Environment > Execute Data Cut-over in Production > Execute Manual Data Entry in Production > Execute Operational Cut-over (Go-Live) | TA | 24

## CLOSE
task | task_details | role | hours
Configurations Documentation | Generate and deliver a configurations document containing the following information: A robust documentation of code, including code snippets, as well as a list of objects that were created or updated, accompanied with a short description of the modification, as well as all integrations. This excludes user interface changes such as form layout updates. | TA | 16
IT Knowledge Transfer | Perform Knowledge Transfer reviewing configurations made by ADVANCE team with Client administrators. | TA | 8
Transition to Post-Live Support (Hypercare) | Conducte Handover Operations > Ensure that there is a seamless transition of support activities from the Project implementation team to the Support Organization. | TA | 4
Hypercare Post-Live Support | Hypercare Post-Go-Live Support > ADVANCE shall staff one (1) full-time resource to provide up to five (5) consecutive business days of post live support to address any defects that arise in Production. Identify and Prioritize Production Defects > Identify and prioritize all defects to be resolved during Hypercare support from the Defect Backlog. Fix and Test Production Defects > Fix and test the prioritized defects from the defect backlog documented during Go-Live and Hypercare support activities. > The objective is to resolve the priority defects identified and ensure the stabilization of the project implementation. | TC | 40
Confirm Operational Support | Review the Hypercare support operational stabilization checklist and record status of each stabilization activity. > The purpose of this activity is to review the Hypercare support operational stabilization checklist and record status of each stabilization activity for reporting and action during Hypercare support. | TA | 4

## OVERLAY
capability | task | task_details | role | hours
Business Analysis | Business Analysis | Responsible for documenting workshop findings. > Commonly referred to as workshop "scribe". | BA | 0
Business Process | Business Process | Facilitates communications, leads and drives workshops, interpret business needs, and defines / solves problems. | BPC | 0
Project Management | Project Management | Maintain project objectives and timelines by providing oversight throughout the lifecycle of the project. | EM | 0
Solution Architect | Technical Architect | Provide technical guidance and oversight throughout the lifecycle of the project. | TA | 0
Business Process Consultant | Business Process Consultant | Business process oversight - responsible for maintaining the technical objectives' alignment with department goals and organizational objectives. | BPC | 0

## PSDS
capability | task | task_details | role | hours | standard | pro | pro_plus | enterprise
|  |  | BPC | 4 | Y | Y | Y | Y
|  |  | BPC | 4 | Y | Y | Y | Y
|  |  | BPC | 4 | Y | Y | Y | Y
|  |  | BPC | 4 | Y | Y | Y | Y
|  |  | BPC | 4 | Y | Y | Y | Y
|  |  | BPC | 4 | Y | Y | Y | Y
|  |  | BPC | 4 | Y | Y | Y | Y
|  |  | BPC | 4 | Y | Y | Y | Y
|  |  | BPC | 4 | Y | Y | Y | Y
|  |  | BPC | 4 | Y | Y | Y | Y
|  |  | BPC | 4 | Y | Y | Y | Y
|  |  | BPC | 4 | N | Y | Y | Y
|  |  | BPC | 4 | N | Y | Y | Y
|  |  | BPC | 4 | N | Y | Y | Y
|  |  | BPC | 4 | N | Y | Y | Y
|  |  | BPC | 4 | N | Y | Y | Y
|  |  | BPC | 4 | N | Y | Y | Y
|  |  | BPC | 4 | N | Y | Y | Y
|  |  | BPC | 4 | N | Y | Y | Y
|  |  | BPC | 4 | N | Y | Y | Y
|  |  | BPC | 4 | N | Y | Y | Y
|  |  | BPC | 4 | N | Y | Y | Y
|  |  | BPC | 4 | N | N | Y | Y
|  |  | BPC | 4 | N | N | N | Y
|  |  | BPC | 4 | N | N | N | Y

## PSDS_BUILD
capability | feature | feature_task_details | role | hours | standard | pro | ent | platform
Customer Service Management | Customer Service Management | Configure CSM as defined in workshops, limited to: > Using the OOTB predefined process and flow of the ServiceNow CSM application and modules > Using the OOTB predefined interoperability and flow of the ServiceNow CSM application, interacting with incident, change, problem, knowledge, service level management and portal > Updating the Customer Service Case Table - up to ten (10) custom fields, up to two (2) business rule, up to two (2) UI actions, up to two (2) client scripts - to support a minimal change to the case interface and workflow > Configure list view of the case form > Configuration of the OOTB related lists (parent / child), providing visibility to OOTB related lists. | TC | 60 | Y | Y | Y | N
Incident Management | Incident Management | Incident - Configure up to five (5) custom fields, up to two (2) views (platform & workspace), up to two (2) business rules, up to two (2) UI actions, and up to two (2) client scripts - to support a minimal change to the IT Agent Workspace user interface and workflow. > Up to five four (4) auto-assignments rules for approval routing and task assignment | TC | 24 | Y | Y | Y | N
Problem Management | Problem Management | Problem - Configure up to five (5) custom fields, up to two (2) views (platform & workspace), up to two (2) business rules, up to two (2) UI actions, and up to two (2) client scripts - to support a minimal change to the IT Agent Workspace UI and workflow. > Up to two (2) auto-assignments rules for approval routing and task assignment | TC | 24 | Y | Y | Y | N
Change Management | Change Management | Change - Configure up to five (5) custom fields, up to two (2) views (platform & workspace), up to two (2) business rules, up to two (2) UI actions, and up to two (2) client scripts - to support a minimal change to the IT Agent Workspace UI* and workflow. > Up to six (6) auto-assignments rules for approval routing and task assignment | TC | 24 | Y | Y | Y | N
Release Management | Release Management |  | TC | 4 | Y | Y | Y | N
Cost Management | Cost Management |  | TC | 4 | Y | Y | Y | N
Asset Management | Asset Management | Configure ITSM Asset Management: > Identify Assets > Configure up to four (4) Asset Categories > Configure the Asset Model hierachy consisting of up to twelve (12) Asset Models > Configure up to two (2) Product Bundles > Use ServiceNow OOTB* "asset states" (i.e, in stock, in transit, in use,...retired, missing) > Asset Inventory - Configure up to two (2) physical stockroom locations in ServiceNow, and up to eight eight (8) virtual stockrooms and up to eight (8) virtual Stockrooms. | TC | 24 | Y | Y | Y | N
Request Management | Request Management | Configure up to "n" number of service catalog items and related request workflows: > Up to five (5) low complexity* > Up to two (2) moderate complexity* > Up to 1 (1) high complexity* | TC | 60 | Y | Y | Y | N
Communities | Communities | WIP | TC | 40 | Y | Y | Y | N
Walk-Up Experience | Walk-Up Experience | WIP | TC | 32 | Y | Y | Y | N
Engagement Messenger | Engagement Messenger | WIP | TC | 40 | Y | Y | Y | N
Digital Portfolio Management | Digital Portfolio Management |  | TC | 4 | Y | Y | Y | N
Public Sector Digital Services Core | Public Sector Digital Services Core | Install and Setup Public Sector Digital Services > Create up to two (2) new case types to manage public service requests. > Create up to twent-four (24) service catalog item record producers for constituents to submit service requests. > Create up to two (2) new case playbooks to automate the service request workflow. | TC | 80 | Y | Y | Y | N
Unversal Request | Unversal Request |  | TC | 4 | Y | Y | Y | N
Universal Request Pro | Universal Request Pro | WIP | TC | 16 | N | Y | Y | N
Outsourced Customer Service | Outsourced Customer Service |  | TC | 4 | N | Y | Y | N
Proactive Customer Service Operations | Proactive Customer Service Operations |  | TC | 4 | N | Y | Y | N
Continual Improvement Management | Continual Improvement Management |  | TC | 4 | N | Y | Y | N
Vendor Manager Workspace | Vendor Manager Workspace |  | TC | 4 | N | Y | Y | N
Mobile Publishing | Mobile Publishing |  | TC | 4 | N | Y | Y | N
DevOps Change Velocity | DevOps Change Velocity |  | TC | 4 | N | Y | Y | N
App Engine Studio | App Engine Studio | WIP | TC | 4 | N | Y | Y | N
Performance Analytics | Performance Analytics | Create / Modify up to two (2) PA dashboards and six (6) PA reports, utilizing out of the box joins only for PSDS per the requirements discussed during workshop sessions and as defined in the design documentation. | TC | 24 | N | Y | Y | N
Predictive Intelligence | Predictive Intelligence |  | TC | 4 | N | Y | Y | N
Virtual Agent | Virtual Agent | Configure virtual agent branding/setup. Configure Virtual Agent for chat with up to 5 topics of small complexity. > 1 layer of questions > Initial question with 0 – 10 choices, each with an informational response > No follow up questions, OR one generic follow up question shown after each response (i.e., would you like to create a incident, do you still need assistance, do you want to contact a live agent, search knowledge base, etc.) [OR] > 1 - 2 layers of questions > Initial question with 0 – 5 choices, each with an informational response or a follow up question > Follow up question with 0 – 2 choices, each with an informational response > No further follow up questions, OR one generic follow up question shown at the end of the conversational path (i.e., would you like to create a case, do you still need assistance, do you want to contact a live agent, search knowledge base, etc.) | TC | 32 | N | Y | Y | N
DevOps Config | DevOps Config |  | TC | 4 | N | Y | Y | N
Workforce Optimization | Workforce Optimization |  | TC | 4 | N | N | Y | N
Process Optimization | Process Optimization |  | TC | 4 | N | N | Y | N
Portal Visits per month (per Fulfiller/Unrestricted User) (Standard) | Portal Visits per month (per Fulfiller/Unrestricted User) (Standard) | 1000/200 Portal visits | TC | 4 | Y | N | N | N
Portal Visits per month (per Fulfiller/Unrestricted User) (Pro) | Portal Visits per month (per Fulfiller/Unrestricted User) (Pro) | 2000/400 Portal visits | TC | 4 | N | Y | N | N
Portal Visits per month (per Fulfiller/Unrestricted User) (Enterprise) | Portal Visits per month (per Fulfiller/Unrestricted User) (Enterprise) | 2000/400 Portal visits | TC | 4 | N | N | Y | N
App Engine Custom Tables (Standard) | App Engine Custom Tables (Standard) | 25 Tables | TC | 4 | Y | N | N | N
App Engine Custom Tables (Pro) | App Engine Custom Tables (Pro) | 100 Tables | TC | 4 | N | Y | N | N
App Engine Custom Tables (Enterprise) | App Engine Custom Tables (Enterprise) | 1000 Tables | TC | 4 | N | N | Y | N
Conversational | Conversational |  | TC |  | N | N | N | Y | PLATFORM INTERFACE
Mobile | Mobile |  | TC |  | N | N | N | Y | PLATFORM INTERFACE
Government Service Management (GSM) Portal | Government Service Management (GSM) Portal | EC Installation: > Pre-Work - Before installing the GSM Portal, ensure an Public Sector Digital Services Core is activated and install any remaining dependent plugins. GSM Configuration limited to: > Up to one (1) GSM Portal. > Modifications to the pre-built GSM Portal layout. > Modify UI elements in alignment with the Client's company color scheme, theme, and branding. | TC | 40 | N | N | N | Y | PLATFORM INTERFACE
Workspaces | Workspaces | Configure CSM/FSM Configurable Workspace view(s) as defined during workshops, limited to: > Setup branding and theming. > Additional modification to views as required within the time alloted for this task. | TC | 24 | N | N | N | Y | PLATFORM INTERFACE
Web Service (API) | Web Service (API) |  | TC |  | N | N | N | Y | PLATFORM INTERFACE
CMDB | CMDB | CMDB Normalization & Reconciliation Configuration: > Develop up to two (2) Normalization mappings and reconciliation rules. Perform Asset / CMDB Data Load & Remediation: > Create up to four (4) import sets and transform maps to support a one-time import of configuration items (CI’s) in a supported format (.csv, spreadsheet, etc.). > Conduct up to two (2) One-Time-Imports into a specific table (i.e. Wireless devices from Oracle DB) Configuration Management Database (CMDB) Configuration > Leverage the OOTB CMDB classes and OOTB Asset Model mappings. > Mapping up to fifteen (15) fields with like for like data from the source system / file to the fields in ServiceNow - a unique identifier from the source system / file must be available. > Leverage the OOTB lifecycle and interdependencies from ServiceNow for CI and Asset. > Configure access controls to CMDB forms and data. | TC | 24 | N | N | N | Y | PLATFORM CORE
CSDM | CSDM | CSDM Enablement: > Migrate life cycle data. This step includes mapping and migrating the legacy life cycle values to the CSDM standard values. > Activate the CSDM Activation plugin [com.snc.cmdb.csdm.activation]. > Create a mapping record for lifecycle migration CSDM Configuration: > Minor modifications to the pre-built CSDM Data Foundations dashboard (if required). | TC | 24 | N | N | N | Y | PLATFORM CORE
Knowledge Management | Knowledge Management | Configure Knowledge Management limited to: > up to one (1) Knowledge Base (KB) re-certification process with up to one (1) corresponding workflow. > Up to two (2) global knowledge bases - end user / customer and fulfiller - with up to two (2) user criteria. > Setup up to one (1) workflow with up to two (2) approval steps enabling a KB article to move to the "published" state. > Up to one (1) knowledge homepage in the EC or EC Pro Service Portal. | TC | 20 | N | N | N | Y | PLATFORM CORE
Service Catalog | Service Catalog | Configure the Service and Product Catalog Taxonomy: > Define catalog categories in a parent-child hierarchy (i.e. Hardware category can contain subcategories for computers and mobile devices). > Up to four (4) new unique catalog categories and up to eight (8) new unique subcategories. | TC | 12 | N | N | N | Y | PLATFORM CORE
Service Level Management (SLAs) | Service Level Management (SLAs) | Configure up to four (4) response driven and up to four (4) resolution driven SLAs - with up to a four (4) tiered priority level - using OOTB status field variables (i.e., start, stop, closed and cancelled) conditions. | TC | 12 | N | N | N | Y | PLATFORM CORE
Notifications | Notifications | Enable/Disable OOTB Notifications for the in-scope applications based on workshop results. Modify content variables and conditions, and create up to two (2) branding templates. | TC | 16 | N | N | N | Y | PLATFORM CORE
Reporting | Reporting | Create / Modify up to two (2) standard dashboards and six (6) standard reports, utilizing out of the box joins only for PSDS per the requirements discussed during workshop sessions and as defined in the design documentation. | TC | 10 | N | N | N | Y | PLATFORM CORE
Surveys & Assessments | Surveys & Assessments | Configure Survey Management as discussed during the workshop sessions and defined in the design documentation. > Up to two (2) survey definitions. | TC | 8 | N | N | N | Y | PLATFORM CORE
Authentication | Authentication | Review and configure the most important methods dor controlling acces to the ServiceNow instance; user authentication, identity verification, and authorztion to control access levels and permissins. > Authentication > Authorization > File attachments > Access by ServiceNow employees (ServieNow support) > Auditing access permissions > Instance identification | TC | 12 | N | N | N | Y | PLATFORM SECURITY & ADMIN
Instance Security Center | Instance Security Center (ISC) | Instance Security Center (ISC) Dashboard Activation / Configuration limited to: > Minor modifications to the ISC Dashboard (i.e., Event Ribbon and Top Recommendations) > Layout and branding configurations | TC | 5 | N | N | N | Y | PLATFORM SECURITY & ADMIN
Subscription Management | Subscription Management | Set up Subscription Management for managing ServiceNow license entitlements and license usage. > Assign the usage admins > Configure the color-code threshold > Map up to four (4) custom applications > Map custom tables > Verify ability to monitor and manage ServiceNow subscriptions | TC | 5 | N | N | N | Y | PLATFORM SECURITY & ADMIN
*OOTB - Out of the box
*UI - User interface
*Low Complexity Catalog items contain up to five (5) variables, do not have dynamic menus or dependent values, do not have more than 1 approval task, do not have scripted Approvals, up to two (2) UI Policies or Client Scripts and do not explicitly necessitate their own unique workflow. Low Complexity Catalog Items typically have less than 5 total activities as part of their workflow, including one (1) task to fulfill the request. > Up to one (1) auto-assignments rules for approval routing and task assignment
*Moderate Complexity Catalog Items contain up to fifteen (15) variables, have dynamic data-driven menus or dependent values, have up to three (3) Approval Steps or require scripted Approvals, and up to five (5) UI Policies or Client Scripts. Moderate Complexity Catalog items typically require their own workflow, however still may share workflows depending on the use case. Moderate Complexity Catalog Items typically have less than 10 total activities as part of their workflow, including up to six (6) tasks to fulfill the request. > Up to five (5) auto-assignments rules for approval routing and task assignment [Book30]Sheet1!$C$31:$D$196
*High Complexity Catalog Items contain up to twenty-five (25) variables, have dynamic data-driven menus or dependent values, have up to five (5) Approval Steps or require scripted Approvals, and up to ten (10) UI Policies or Client Scripts. High Complexity Catalog Items require their own workflow and can have up to twenty (20) total activities, including up to ten (10) tasks as part of their workflow with multiple logic paths, to fulfill the request. > Up to ten (10) auto-assignments rules for approval routing and task assignment
Application scoping template (idea)
> Create up to two (2) list views - classic (1 view) and workspace (1 view) > Add up to four (4) fields to classic and workspace views > Add category and reference values > Enable auto assignment of incidents
PSDS Licensing
https://www.servicenow.com/content/dam/servicenow-assets/public/en-us/doc-type/other-document/entitlements/sn-public-sector-digital-services.pdf
Add ons use '$' to specify -> need to figure out how to filter

## PF_BUILD
capability | feature | feature_task_details | role | hours | u_std | u_mod | u_cx
Consistency & Scalability | CMDB | CMDB Normalization & Reconciliation Configuration: > Develop up to two (2) Normalization mappings and reconciliation rules. Perform Asset / CMDB Data Load & Remediation: > Create up to four (4) import sets and transform maps to support a one-time import of configuration items (CI’s) in a supported format (.csv, spreadsheet, etc.). > Conduct up to two (2) One-Time-Imports into a specific table (i.e. Wireless devices from Oracle DB) Configuration Management Database (CMDB) Configuration > Leverage the OOTB CMDB classes and OOTB Asset Model mappings. > Mapping up to fifteen (15) fields with like for like data from the source system / file to the fields in ServiceNow - a unique identifier from the source system / file must be available. > Leverage the OOTB lifecycle and interdependencies from ServiceNow for CI and Asset. > Configure access controls to CMDB forms and data. | TC | 24 | Y | Y | Y
Consistency & Scalability | CSDM | CSDM Enablement: > Migrate life cycle data. This step includes mapping and migrating the legacy life cycle values to the CSDM standard values. > Activate the CSDM Activation plugin [com.snc.cmdb.csdm.activation]. > Create a mapping record for lifecycle migration CSDM Configuration: > Minor modifications to the pre-built CSDM Data Foundations dashboard (if required). | TC | 24 | N
Consistency & Scalability | Knowledge Management | Configure Knowledge Management limited to: > up to one (1) Knowledge Base (KB) re-certification process with up to one (1) corresponding workflow. > Up to two (2) global knowledge bases - end user / customer and fulfiller - with up to two (2) user criteria. > Setup up to one (1) workflow with up to two (2) approval steps enabling a KB article to move to the "published" state. > Up to one (1) knowledge homepage in the EC or EC Pro Service Portal. | TC | 20 | Y
Consistency & Scalability | Service Catalog | Configure the Service and Product Catalog Taxonomy: > Define catalog categories in a parent-child hierarchy (i.e. Hardware category can contain subcategories for computers and mobile devices). > Up to four (4) new unique catalog categories and up to eight (8) new unique subcategories. | TC | 12 | Y
Productivity | Workspace(s) | Configure CSM/FSM Configurable Workspace view(s) as defined during workshops, limited to: > Setup branding and theming > Limited modifications to OOTB components in support of in scope applications (i.e., Incident Management, Problem Management, etc.). | TC | 24 | Y | Y | Y
Productivity | Reporting | Create up to two (2) dashboards and six (6) simple reports, utilizing out of the box joins only for ITSM per the requirements determined in workshops. > Limited modifications to OOTB dashboards and reports to support user requirements as defined in the project design documentation*. | TC | 16 | Y | Y | Y
Productivity | Service Level Management (SLAs) | Configure up to four (4) response driven and up to four (4) resolution driven SLAs - with up to a four (4) tiered priority level - using OOTB status field variables (i.e., start, stop, closed and cancelled) conditions. | TC | 12 | Y | Y | Y
Productivity | Skills Management |  | TC | 4 | N | Y | Y
Productivity | Workforce Optimization (WO) |  | TC | 4 | N | Y | Y
Intelligence | Machine Learning (ML) |  | TC | 4 | N | Y | Y
Intelligence | NLP / NLU / NLQ |  | TC | 4 | N | Y | Y
Intelligence | User Experience (UX) Analytics | Activate the UX analytics PA dashboard plugin. > Zero (0) or very limited modifications to OOTB components. | TC | 4 | Y | Y | Y
Intelligence | Performance Analytics (PA) | Create / Modify up to two (2) PA dashboards and six (6) PA reports, utilizing out of the box joins to support user requirements as defined in the project design documentation | TC | 4 | Y | Y | Y
Intelligence | Process Mining |  | TC | 4 | N | Y | Y
Engagement | Conversational Interfaces |  | TC | 4 | N | Y | Y
Engagement | Employee Center (EC) Service Portal | EC Installation: > Pre-Work - Before installing Employee Center, ensure an employee-facing service delivery product is installed (i.e., ITSM). > Verify plugin activation for; Employee Center Core [sn_hr_sp], Employee Experience Taxonomy [sn_ect], and Employee Experience Foundation [sn_ex_emp_fd]. EC Configuration limited to: > Up to one (1) EC Portal. > Modifications to the pre-built EC Portal layout. > Modify UI elements in alignment with the Client's company color scheme, theme, and branding. | TC | 24 | Y | Y | Y
Engagement | Mobile |  | TC | 4 | N | Y | Y
Engagement | Playbook Experiences |  | TC | 4 | N | Y | Y
Automation | Flow Designer |  | TC | 4 | N | Y | Y
Automation | Process Automation Designer |  | TC | 4 | N | Y | Y
Automation | Decision Builder |  | TC | 4 | N | Y | Y
Automation | Advanced Work Assignment |  | TC | 4 | N | Y | Y
Automation | Automation Engine |  | TC | 4 | N | Y | Y
Security | Platform Encryption |  | TC | 4 | N | Y | Y
Security | Data Anonymization |  | TC | 4 | N | Y | Y
Security | Secrets Management |  | TC | 4 | N | Y | Y
Security | Code Signing |  | TC | 4 | N | Y | Y
*Project design documentation is created during the workshop and design project phases.

## ITSM_BUILD
capability | feature | feature_task_details | role | hours | standard | pro | pro_plus | enterprise
Incident | Incident Management - Core | Incident - Configure up to five (5) custom fields, up to two (2) views (platform & workspace), up to two (2) business rules, up to two (2) UI actions, and up to two (2) client scripts - to support a minimal change to the IT Agent Workspace user interface and workflow. > Up to five four (4) auto-assignments rules for approval routing and task assignment | TC | 4 | Y | Y | Y | Y
Change | Change Management - Core | Change - Configure up to five (5) custom fields, up to two (2) views (platform & workspace), up to two (2) business rules, up to two (2) UI actions, and up to two (2) client scripts - to support a minimal change to the IT Agent Workspace UI* and workflow. > Up to six (6) auto-assignments rules for approval routing and task assignment | TC | 4 | Y | Y | Y | Y
Release | Release Management - Core | PRESALES PLACEHOLDER | TC | 4 | Y | Y | Y | Y
Problem | Problem Management - Core | Problem - Configure up to five (5) custom fields, up to two (2) views (platform & workspace), up to two (2) business rules, up to two (2) UI actions, and up to two (2) client scripts - to support a minimal change to the IT Agent Workspace UI and workflow. > Up to two (2) auto-assignments rules for approval routing and task assignment | TC | 4 | Y | Y | Y | Y
Request | Request & Service Catalog | Configure up to "n" number of service catalog items and related request workflows: > Up to five (5) low complexity* > Up to two (2) moderate complexity* > Up to 1 (1) high complexity* | TC | 4 | Y | Y | Y | Y
Asset | ITSM Asset Management | Configure ITSM Asset Management: > Identify Assets > Configure up to four (4) Asset Categories > Configure the Asset Model hierachy consisting of up to twelve (12) Asset Models > Configure up to two (2) Product Bundles > Use ServiceNow OOTB* "asset states" (i.e, in stock, in transit, in use,...retired, missing) > Asset Inventory - Configure up to two (2) physical stockroom locations in ServiceNow, and up to eight eight (8) virtual stockrooms and up to eight (8) virtual Stockrooms. | TC | 4 | Y | Y | Y | Y
Cost | Cost |  | TC | 4 | Y | Y | Y | Y
Walk-Up Experience | Walk-Up Experience | PRESALES PLACEHOLDER | TC | 4 | Y | Y | Y | Y
Universal Request | Universal Request |  | TC | 4 | Y | Y | Y | Y
Digital Portfolio Management | Digital Portfolio Management |  | TC | 4 | Y | Y | Y | Y
App Engine Starter 25 | App Engine Starter 25 |  | TC | 4 | Y | Y | Y | Y
Continual Improvement | Continual Improvement | task details | TC | 4 | N | Y | Y | Y
DevOps Change Velocity | DevOps Change Velocity | task details | TC | 4 | N | Y | Y | Y
Vendor Manager Workspace | Vendor Manager Workspace | task details | TC | 4 | N | Y | Y | Y
Financial Modelling | Financial Modelling | task details | TC | 4 | N | Y | Y | Y
Mobile Publishing | Mobile Publishing | task details | TC | 4 | N | Y | Y | Y
Predictive Intelligence | Predictive Intelligence | task details | TC | 4 | N | Y | Y | Y
Virtual Agent | Virtual Agent | task details | TC | 4 | N | Y | Y | Y
PA for ITSM | PA for ITSM | task details | TC | 4 | N | Y | Y | Y
Universal Request Pro | Universal Request Pro | task details | TC | 4 | N | Y | Y | Y
App Engine Starter 50 | App Engine Starter 51 | task details | TC | 4 | N | Y | Y | Y
DevOps Config | DevOps Config | task details | TC | 4 | N | Y | Y | Y
Virtual Agent Optimize | Virtual Agent Optimize | task details | TC | 4 | N | N | Y | Y
Workforce Optimization | Workforce Optimization | task details | TC | 4 | N | N | N | Y
Process Optimization | Process Optimization | task details | TC | 4 | N | N | N | Y
*OOTB - Out of the box
*UI - User interface
*Low Complexity Catalog items contain up to five (5) variables, do not have dynamic menus or dependent values, do not have more than 1 approval task, do not have scripted Approvals, up to two (2) UI Policies or Client Scripts and do not explicitly necessitate their own unique workflow. Low Complexity Catalog Items typically have less than 5 total activities as part of their workflow, including one (1) task to fulfill the request. > Up to one (1) auto-assignments rules for approval routing and task assignment
*Moderate Complexity Catalog Items contain up to fifteen (15) variables, have dynamic data-driven menus or dependent values, have up to three (3) Approval Steps or require scripted Approvals, and up to five (5) UI Policies or Client Scripts. Moderate Complexity Catalog items typically require their own workflow, however still may share workflows depending on the use case. Moderate Complexity Catalog Items typically have less than 10 total activities as part of their workflow, including up to six (6) tasks to fulfill the request. > Up to five (5) auto-assignments rules for approval routing and task assignment [Book30]Sheet1!$C$31:$D$196
*High Complexity Catalog Items contain up to twenty-five (25) variables, have dynamic data-driven menus or dependent values, have up to five (5) Approval Steps or require scripted Approvals, and up to ten (10) UI Policies or Client Scripts. High Complexity Catalog Items require their own workflow and can have up to twenty (20) total activities, including up to ten (10) tasks as part of their workflow with multiple logic paths, to fulfill the request. > Up to ten (10) auto-assignments rules for approval routing and task assignment
Application scoping template (idea)
> Create up to two (2) list views - classic (1 view) and workspace (1 view) > Add up to four (4) fields to classic and workspace views > Add category and reference values > Enable auto assignment of incidents

## PF
capability | task | task_details | role | hours | u_std | u_mod | u_cx
Consistency & Scalability | CMDB | WORKSHOP | BPC | 4 | Y | Y | Y
Consistency & Scalability | CSDM | WORKSHOP | BPC | 4 | N
Consistency & Scalability | Knowledge Management | WORKSHOP | BPC | 4 | Y
Consistency & Scalability | Service Catalog | WORKSHOP | BPC | 4 | Y
Productivity | Workspace(s) | WORKSHOP | BPC | 4 | Y | Y | Y
Productivity | Reports & Dashboards | WORKSHOP | BPC | 4 | Y | Y | Y
Productivity | Service Level Management (SLAs) | WORKSHOP | BPC | 4 | Y | Y | Y
Productivity | Skills Management | WORKSHOP | BPC | 4 | N | Y | Y
Productivity | Workforce Optimization (WO) | WORKSHOP | BPC | 4 | N | Y | Y
Intelligence | Machine Learning (ML) | WORKSHOP | BPC | 4 | N | Y | Y
Intelligence | NLP / NLU / NLQ | WORKSHOP | BPC | 4 | N | Y | Y
Intelligence | User Experience (UX) Analytics | WORKSHOP | BPC | 4 | Y | Y | Y
Intelligence | Performance Analytics (PA) | WORKSHOP | BPC | 4 | Y | Y | Y
Intelligence | Process Mining | WORKSHOP | BPC | 4 | N | Y | Y
Engagement | Conversational Interfaces | WORKSHOP | BPC | 4 | N | Y | Y
Engagement | Employee Center (EC) Service Portal) | WORKSHOP | BPC | 4 | Y | Y | Y
Engagement | Mobile | WORKSHOP | BPC | 4 | N | Y | Y
Engagement | Playbook Experiences | WORKSHOP | BPC | 4 | N | Y | Y
Automation | Flow Designer | WORKSHOP | BPC | 4 | N | Y | Y
Automation | Process Automation Designer | WORKSHOP | BPC | 4 | N | Y | Y
Automation | Decision Builder | WORKSHOP | BPC | 4 | N | Y | Y
Automation | Advanced Work Assignment | WORKSHOP | BPC | 4 | N | Y | Y
Automation | Automation Engine | WORKSHOP | BPC | 4 | N | Y | Y
Security | Platform Encryption | WORKSHOP | BPC | 4 | N | Y | Y
Security | Data Anonymization | WORKSHOP | BPC | 4 | N | Y | Y
Security | Secrets Management | WORKSHOP | BPC | 4 | N | Y | Y
Security | Code Signing | WORKSHOP | BPC | 4 | N | Y | Y

## ITSM
capability | task | task_details | role | hours | standard | pro | pro_plus | enterprise
Incident | Incident | task details | BPC | 4 | Y | Y | Y | Y
Change | Change | task details | BPC | 4 | Y | Y | Y | Y
Release | Release | task details | BPC | 4 | Y | Y | Y | Y
Problem | Problem | task details | BPC | 4 | Y | Y | Y | Y
Request | Request | task details | BPC | 4 | Y | Y | Y | Y
Asset | Asset | task details | BPC | 4 | Y | Y | Y | Y
Cost | Cost | task details | BPC | 4 | Y | Y | Y | Y
Walk-Up Experience | Walk-Up Experience | task details | BPC | 4 | Y | Y | Y | Y
Universal Request | Universal Request | task details | BPC | 4 | Y | Y | Y | Y
Digital Portfolio Management | Digital Portfolio Management | task details | BPC | 4 | Y | Y | Y | Y
App Engine Starter 25 | App Engine Starter 25 | task details | BPC | 4 | Y | Y | Y | Y
Continual Improvement | Continual Improvement | task details | BPC | 4 | N | Y | Y | Y
DevOps Change Velocity | DevOps Change Velocity | task details | BPC | 4 | N | Y | Y | Y
Vendor Manager Workspace | Vendor Manager Workspace | task details | BPC | 4 | N | Y | Y | Y
Financial Modelling | Financial Modelling | task details | BPC | 4 | N | Y | Y | Y
Mobile Publishing | Mobile Publishing | task details | BPC | 4 | N | Y | Y | Y
Predictive Intelligence | Predictive Intelligence | task details | BPC | 4 | N | Y | Y | Y
Virtual Agent | Virtual Agent | task details | BPC | 4 | N | Y | Y | Y
PA for ITSM | PA for ITSM | task details | BPC | 4 | N | Y | Y | Y
Universal Request Pro | Universal Request Pro | task details | BPC | 4 | N | Y | Y | Y
App Engine Starter 50 | App Engine Starter 51 | task details | BPC | 4 | N | Y | Y | Y
DevOps Config | DevOps Config | task details | BPC | 4 | N | Y | Y | Y
Virtual Agent Optimize | Virtual Agent Optimize | task details | BPC | 4 | N | N | Y | Y
Workforce Optimization | Workforce Optimization | task details | BPC | 4 | N | N | N | Y
Process Optimization | Process Optimization | task details | BPC | 4 | N | N | N | Y

## HRSD
capability | task | task_details | role | hours | pro_v2 | ent_v2 | ec_pro | p_opt_hrsd
Case Knowledge Management | task | task details | pre_sales | 4 | Y | Y | Y | Y
Continual Improvement | task | task details | pre_sales | 4 | Y | Y | Y | Y
Employee Center Pro | task | task details | pre_sales | 4 | Y | Y | Y | Y
Lifecycle Events | task | task details | pre_sales | 4 | Y | Y | Y | Y
Mobile Publishing | task | task details | pre_sales | 4 | Y | Y | Y | Y
Universal Request | task | task details | pre_sales | 4 | Y | Y | Y | Y
Universal Request Pro | task | task details | pre_sales | 4 | Y | Y | Y | Y
Predictive Intelligence | task | task details | pre_sales | 4 | Y | Y | Y | Y
Virtual Agent | task | task details | pre_sales | 4 | Y | Y | Y | Y
PA for HRSD | task | task details | pre_sales | 4 | Y | Y | Y | Y
Communities | task | task details | pre_sales | 4 | Y | Y | Y | Y
App Egine Starter 15 | task | task details | pre_sales | 4 | Y | Y | Y | Y
Enterprise Onboarding & Transitions | task | task details | pre_sales | 4 | N | Y | Y | Y
Employee Journey Management | task | task details | pre_sales | 4 | N | Y | Y | Y
Employee Center Professional | task | task details | pre_sales | 4 | N | Y | Y | Y
Process Optimization for HRSD | task | task details | pre_sales | 4 | N | Y | Y | Y

## HRSD_BUILD
capability | feature | feature_task_details | role | hours | pro_v2 | ent_v2 | ec_pro | p_opt_hrsd
Case Knowledge Management | task | task details | pre_sales | 4 | Y | Y | Y | Y
Continual Improvement | task | task details | pre_sales | 4 | Y | Y | Y | Y
Employee Center Pro | task | task details | pre_sales | 4 | Y | Y | Y | Y
Lifecycle Events | task | task details | pre_sales | 4 | Y | Y | Y | Y
Mobile Publishing | task | task details | pre_sales | 4 | Y | Y | Y | Y
Universal Request | task | task details | pre_sales | 4 | Y | Y | Y | Y
Universal Request Pro | task | task details | pre_sales | 4 | Y | Y | Y | Y
Predictive Intelligence | task | task details | pre_sales | 4 | Y | Y | Y | Y
Virtual Agent | task | task details | pre_sales | 4 | Y | Y | Y | Y
PA for HRSD | task | task details | pre_sales | 4 | Y | Y | Y | Y
Communities | task | task details | pre_sales | 4 | Y | Y | Y | Y
App Egine Starter 15 | task | task details | pre_sales | 4 | Y | Y | Y | Y
Enterprise Onboarding & Transitions | task | task details | pre_sales | 4 | N | Y | Y | Y
Employee Journey Management | task | task details | pre_sales | 4 | N | Y | Y | Y
Employee Center Professional | task | task details | pre_sales | 4 | N | Y | Y | Y
Process Optimization for HRSD | task | task details | pre_sales | 4 | N | Y | Y | Y

## ROLES_RATES
role | role_name | role_description | std_rate | discount | discount % | rate
EM | Engagement Manager | add role desc | 200 | 0 | 0 | 0
BPC | Business Process Consultant | add role desc | 250 | 0 | 0 | 0
BA | Business Analyst | add role desc | 155 | 0 | 0 | 0
TA | Technical Architect | add role desc | 195 | 0 | 0 | 0
TC | Technical Consultant | add role desc | 175 | 0 | 0 | 0
TCO | Technical Consultant (Offshore) | add role desc | 115 | 0 | 0 | 0
QAE | Quality Assurance Engineer | add role desc | 115 | 0 | 0 | 0
TAM (MS) | Technical Account Manager | managed services role | 115 | 0 | 0 | 0

## ASPEN
team_class | task | task_details | role | hours | aspen | b | c | d
Management |  |  | TC | 240 | Y
Operational Support Services (OSS) | Regular Maintenance - OSS | Clones and instance operational support: > Clone from PROD ->UAT -> DEV for Instance consistency > Regular Patching > Maintain Data Consistency > HealthScan/Annual Upgrades | TC | 500 | Y
Enhacements | DEV - Enhancements | Enhancement Task Backlog Development: > Develop as per User Stories > SME Validation of development > SME shares feedback > Developers address feedback > SME Sign off on development > Update sets are promoted to TEST > Change Request is Documented | TC | 3120 | Y
Enhacements | STAGE - Enhancements | Enhancement Task Backlog Staging: > UAT will begin Testing > Developers address any defects > UAT Signs Off > Update sets are promoted to PROD > No net new development > Code Review in TEST > Change Request is Approved > Daily Development Cadence | TC | 1248
Enhacements | PROD - Enhancements | Enhancement Task Backlog Push to PROD: > SMEs/UAT Validate development. > Defects are raised if anything not working as expected. > Defects are developed in Dev instance and follow same cadence as for any new development. > No net new development in PROD until initiating another release cycle from DEV. | TC | 832
Upgrades | Upgrades | Assist with up to two (2) ServiceNow instance upgrades: > Step 1 - Read the release notes and plan your upgrade. > Step 2 - Complete planning tasks. > Step 3 - Verify upgrade configurations and schedule the development instance upgrade in Now Support. > Step 4 - Upgrade and validate the development instance. > Step 5 - If applicable: Upgrade and validate your other non-production. instances, such as the "Test" instance. > Step 6 - Prepare to upgrade the production instance. > Step 7 - Upgrade the production instance. | TA | 160 | Y
Consultancy Services |  |  | BPC | 320 | Y
Transition |  |  | TA | 160 | Y
Training |  | Trainign prepartion > Create training materials > Training sessions Training shall be performed in English | BPC | 240 | Y
Change Management |  |  | TA | 160 | Y
Other | Backlog | Event Management Configuration > Event collection and correlation configuration > Event processing configuration > Service Impact configuration > Alert intelligence configuration > Alert automation configuration > Anomoly detection configuration | TC |  | Y
|  |  | Total Hours | 6980
minus overlay
NOTES
FTE specify
Hour burn down process
Blended rate
DEV
Breakdown 12 months into (working) days, weeks, hours. (and holidays)
Assumes full resource bench no sick days
Split evenly acrosse tasks (testing not realistic)
Then look at it with "thumb in air approach"
Math to determine hours dispersment
Scope project normally and look at real actuals, determine approach
Chart breakdown by team classifcations
Chart breakdown by role
Sample timeline
Scaling up (BPC or Process Consulting) w/ at least 2-weeks notice.
Scaling out (Add resources to spread workload across more servers) 1-week notice?
Notice = task submission (ideally via an Advance portal - no current capability) > Discuss w/ Mark L and Parshant for future MS offering approach
MATH
|  | Working DAYS in US (same in SA) | 260 | days
|  | Hours for 1 FTE | 2080 | hours
|  | Number of FTEs | 7
|  | Billable Hours | 14560 | hours
|  | Blended Rate | 175
|  | Grand Total | 2548000
|  | Working WEEKS in year | 52 | weeks
|  | Overlay EM % |  | hours
|  | Overlay TA % |  | hours
|  | Overlay TAM (15 min daily call) * working days in year (260) | 65 | hours
|  | Overlay (60 min code review - WED) * working weeks in year | 52 | hours
|  | Overlay (60 min change control - THURS) * working weeks in year | 52 | hours
|  | Overlay (60 min weekly deployment - FRI) * working weeks in year | 52 | hours
|  | FTE BACKLOG (always 2 - "queing theory" | 2
All working hours outside of WED-FRI are dev hours
|  | 2.5 days dev | 7280 | 20
|  | 1.5 days stage | 1248 | 12
|  | 1 day deploy | 832 | 8
|  |  | 9360 | total backlog work
|  |  | 5200 | delta

## ASPEN_NOTES
team_class | task | task_details | role | hours | aspen | b | c | d
Management | Instance Clone Back | Clone back ServiceNow Instance for consistency > Clone back post go-live > When: Once a month or after Major Releases > Why: To keep Sub Instances consistent with PROD > How: Proper communication and process in place to manage this > Communicate with developers to save the work in DEV/STAGE > Communicate with Process Owners to ensure testing/QA is not impacted > Run Scripts to turn off email notifications/Remove Sensitive data etc. | TC | 4 | Y
Management | Subscription Management | Assist the Client with installing the Subscription Management ServiceNow portal. > Assist with license optimization and license forecasting. | TC | 4 | Y
Management | Portal Security | Below are a few example areas that our portal security Technical Consultant can support GTL: > Assess all portals and portal pages across both ServiceNow instances. > Review & assess current LDAP for User Profile Management > Review & assess current ACL (Access Control List) > Review & assess current Single Sign-On > Define Use Cases based on user personas > Propose remediations based on assessment > Implement remediations > Provide detailed documentation for any configuration > Provide training & guidance for any new configuration | TC | 4 | Y
Management | Microsoft SCCM (or similar) Service Graph Connector Integration Maintenance | Maintain or configure the Service Graph connector for one (1) instance of Microsoft SCCM. > Setup instance and authentication. > Data Mapping four up to two (2) Asset classes (Hardware, Software). > Configure the synch schedule. > Other required enhancements as they arise. | TC | 40
Management | Request and Service Catalog | Configure up to "n" number of service catalog items and related request workflows: > Low complexity > Moderate complexity > High complexity | TC | 500
Management | Foundational Data / Location Onboarding | Foundational Data Configuration; Departments, Locations, Companies, Users, Groups, Group Members, Assign Roles. > Upload data from an external data source into an import set. You can use a CSV, XLS, or XML file as the external data source. > Create a transform map, that is, a field mapping between the columns of the import set and the columns of the target table Department [cmn_department]. > Perform the data transfer from the import set table to the target table by executing the transform map. > Verify that the data records are imported into the target table. > Onboard other business locations. |  | 80
Operational Support Services (OSS) | Regular Maintenance - OSS | Clones and instance operational support: > Clone from PROD ->UAT -> DEV for Instance consistency > Regular Patching > Maintain Data Consistency > HealthScan/Annual Upgrades | TC | 500 | Y
Operational Support Services (OSS) | Issue Resolution - OSS | Resolve any defects/issues raised by users. | TC | 500 | Y
Operational Support Services (OSS) | Continuous Improvement - OSS | Continuously learn from user feedback and improve via enhancements to existing development. | TC | 500 | Y
Operational Support Services (OSS) | Change Management, Governance & Best Practices - OSS |  | TC | 250 | Y
Enhacements | DEV - Enhancements | Enhancement Task Backlog Development: > Develop as per User Stories > SME Validation of development > SME shares feedback > Developers address feedback > SME Sign off on development > Update sets are promoted to TEST > Change Request is Documented | TC |  | Y
Enhacements | STAGE - Enhancements | Enhancement Task Backlog Staging: > UAT will begin Testing > Developers address any defects > UAT Signs Off > Update sets are promoted to PROD > No net new development > Code Review in TEST > Change Request is Approved > Daily Development Cadence | TC | 500
Enhacements | PROD - Enhancements | Enhancement Task Backlog Push to PROD: > SMEs/UAT Validate development. > Defects are raised if anything not working as expected. > Defects are developed in Dev instance and follow same cadence as for any new development. > No net new development in PROD until initiating another release cycle from DEV. | TC | 500
Upgrades | Step 1 (Upgrade) - Plan | Assist with up to two (2) ServiceNow instance upgrades. Step 1 - Read the release notes and plan your upgrade. > Review the San Diego release notes for the target ServiceNow feature release and patch, in addition to product and release documentation. > Review the ServiceNow Upgrade Planning Checklist | TA | 8 | Y
Upgrades | Step 2 (Upgrade) - Plan | Step 2 - Complete planning tasks: > Confirm which ServiceNow instances are in-scope for upgrade. > Based on the San Diego release notes and other release materials, determine new functionality or notable changes that need to be validated after the upgrade. > Create a project plan for cloning, upgrading, and testing. > Identify the core team of testers, power users, and key stakeholders required to validate functionality in the ServiceNow instances before and after the upgrade. > Confirm whether there are any change freeze windows impacting the timing for environment clones or upgrades. For example, end quarter. > Confirm the testing scope and approach. > Create a comprehensive test plan including test cases for all core instance functionality and integrations. > Confirm the method for tracking any defects identified during testing. Create a high-level implementation plan that covers: > The sequence and timing to upgrade non-production and production instances > The instances to be cloned > The instance to be used for integration testing. | TA | 8 | Y
Upgrades | Step 3 (Upgrade) - Plan | Step 3 - Verify upgrade configurations and schedule the development instance upgrade in Now Support. > Check the configuration of the Check distribution for possible upgrade scheduled job to view how often and when it runs. > Verify that the Check distribution for possible upgrade sys_trigger is set properly for upgrading. > Verify that the Check database for possible upgrade sys_trigger is set properly for upgrading. > Schedule the upgrade in Now Support. > If applicable, request a version entitlement. | TC | 8 | Y
Upgrades | Step 4 (Upgrade) - Plan | Step 4 - Upgrade and validate the development instance > Using the Upgrade Monitor, monitor the upgrade to the Client's instance and validate that the upgrade to the development instance is complete. > After the upgrade for your development instance is complete, process the skipped records list in the Upgrade Monitor. > Identify update sets. > Before and after upgrading, conduct smoke tests on the Client's development instance. Use the comprehensive test plan to perform functional testing. | TC | 32 | Y
Upgrades | Step 5 (Upgrade) - Plan | Step 5 - If applicable: Upgrade and validate your other non-production instances, such as the "Test" instance > On your production instance, create a system clone and select your development instance as the Target instance. > Schedule the non-production upgrade in Now Support and verify your upgrade configurations. > Validate that the upgrade to your non-production instance is complete. > Install any optional plugins that were installed on your development instance. > Install any custom applications and post-upgrade fix scripts that you need. > Install update sets. > Perform functional testing and monitor the performance of your instance. | TC | 32 | Y
Upgrades | Step 6 (Upgrade) - Prepare "PROD" Instance Upgrade | Step 6 - Prepare to upgrade the production instance > Confirm sign-off from IT and Business stakeholders that all non-production instance defects have been fixed and validated in update sets. > Confirm the core team of key stakeholders required to validate functionality in the ServiceNow instance after the production upgrade. > Confirm coverage for Day 1 support post-upgrade. > Create a Production Upgrade Implementation Plan that includes all upgrade steps, roles and responsibilities, communication plans, key contacts, support coverage for Day 1, and so forth. > Schedule a walkthrough and sign-off of the Implementation Plan with key stakeholders and the core team. > Submit and obtain approvals for change records as required by the organization change process. > Send a communication to key stakeholders and end users with details for the production upgrade outage, new features, and so forth. > Profile the performance of the Client's "PROD" instance before upgrading. > Use the ServiceNow Performance homepage to document the performance of your instance before the upgrade. > During the clone process, perform functional testing and monitor the performance of the Client's "PROD" instance. | TC | 48 | Y
Upgrades | Step 7 (Upgrade) - Upgrade "PROD" Instance | Step 7 - Upgrade the production instance > Schedule the upgrade in Now Support. > If applicable, request a version entitlement. > Monitor the upgrade to your instance and validate that the upgrade to your production instance is complete. > Apply any update sets and post-upgrade fix scripts that you have. > Validate and test the Client's "PROD" instance by conducting user acceptance testing (UAT). Verify with all key stakeholders that the system is performing properly after production upgrade, and key functionality is available. | TC | 24 | Y
Consultancy Services |  |  | BPC | 320 | Y
Transition |  |  | TA | 320 | Y
Training |  | Trainign prepartion > Create training materials > Training sessions Training shall be performed in English | BPC | 320 | Y
Change Management |  |  | TA | 160 | Y
Other | Backlog | Event Management Configuration > Event collection and correlation configuration > Event processing configuration > Service Impact configuration > Alert intelligence configuration > Alert automation configuration > Anomoly detection configuration | TC |  | Y
|  |  | Total Hours | 4662
NOTES
FTE specify
Hour burn down process
Blended rate
DEV
Breakdown 12 months into (working) days, weeks, hours. (and holidays)
Assumes full resource bench no sick days
Split evenly acrosse tasks (testing not realistic)
Then look at it with "thumb in air approach"
Math to determine hours dispersment
Scope project normally and look at real actuals, determine approach
Chart breakdown by team classifcations
Chart breakdown by role
Sample timeline
Scaling up (BPC or Process Consulting) w/ at least 2-weeks notice.
Scaling out (Add resources to spread workload across more servers) 1-week notice?
Notice = task submission (ideally via an Advance portal - no current capability) > Discuss w/ Mark L and Parshant for future MS offering approach
MATH
|  | Working DAYS in US (same in SA) | 260 | days
|  | Hours for 1 FTE | 2080 | hours
|  | Number of FTEs | 3
|  | Billable Hours | 6240 | hours
|  | Blended Rate | 175
|  | Grand Total | 1092000
|  | Working WEEKS in year | 52 | weeks
|  | Overlay EM % |  | hours
|  | Overlay TA % |  | hours
|  | Overlay TAM (15 min daily call) * working days in year (260) | 65 | hours
|  | Overlay (60 min code review - WED) * working weeks in year | 52 | hours
|  | Overlay (60 min change control - THURS) * working weeks in year | 52 | hours
|  | Overlay (60 min weekly deployment - FRI) * working weeks in year | 52 | hours
|  | FTE BACKLOG (always 2 - "queing theory" | 2
All working hours outside of WED-FRI are dev hours
|  | 2.5 days dev | 3120 | 20
|  | 1.5 days stage | 1248 | 12
|  | 1 day deploy | 832 | 8
|  |  | 5200 | total backlog work
|  |  | 1040 | delta

## ASPEN_OVY
capability | task | task_details | role | hours
Business Analysis | Business Analysis | Responsible for documenting workshop findings. > Commonly referred to as workshop "scribe". | BA | 0
Business Process Consultant | Business Process | Business process oversight - responsible for maintaining the technical objectives' alignment with department goals and organizational objectives. | BPC | 0
Project Management | Project Management | Maintain project objectives and timelines by providing oversight throughout the lifecycle of the project. | EM | 0
Solution Architect | Technical Architect | Provide technical guidance and oversight throughout the lifecycle of the project. | TA | 0
Technical Account Management | Daily Standup Call | Review Development Status (15 minutes): > Updates/Roadblocks/Issues > Not for solutioning > Not for detailed discussion | TAM | 0
Code Review (WED) | Code Review | Review Update Sets (60 minutes): > Core Tables are not touched > Coding per best practices > Update Set doesn’t have issues | TA | 0
Change Control (THURS) | Change Control | Sign Off on Changes (60 minutes): > Review if process was followed properly > Change impact/conflicts > Rollback plan if needed > Resources for Change Support | TA | 0
Weekly Deployment (FRI) | Weekly Deployment | Deploy Update Sets (60 minutes) > Deploy Update Sets from Stage to PROD > Validate functionality as per development > Communicate Deployment | TA | 0
Technical Consultant | Developer | Assist and communicate with the TAM, EM, and Client during each steps in the ADVANCE CI/CD pipeline. | TC | 0
QA | UAT | Test the changes in a pre-prod instance and be available during Client UAT for immediate remediation of any issues. ADVANCE will support UAT by remediating prioritized defects and providing high-level explanations of the applications and associated workflow to individuals tasked to test the system operation. UAT issues will be triaged and assigned one of the following types: 1. Defect: there is a flaw with the configuration, which ADVANCE will correct 2. Training: the issue is due to a tester misunderstanding of functionality and will be corrected via training/education 3. Enhancement: the issue submitted is not functionality that was agreed upon in the FRO and was therefore never configured and is out of scope All resolved defects would then be retested to ensure completeness of the resolution. Testing will be done on the in-scope ServiceNow applications, processes, workflows, and integrations. | QAE | 0
Overlay EM % |  | hours
Overlay TA % |  | hours
Overlay TAM (15 min daily call) * working days in year (260) | #VALUE! | hours
Overlay (60 min code review - WED) * working weeks in year | 0 | hours
Overlay (60 min change control - THURS) * working weeks in year | 0 | hours
Overlay (60 min weekly deployment - FRI) * working weeks in year | 0 | hours

## ASPEN_ROLES_RATES
role | role_name | role_description | std_rate | discount | discount % | rate
EM | Engagement Manager | add role desc | 200 | 0 | 0 | 0
BPC | Business Process Consultant | add role desc | 250 | 0 | 0 | 0
BA | Business Analyst | add role desc | 155 | 0 | 0 | 0
TA | Technical Architect | add role desc | 195 | 0 | 0 | 0
TC | Technical Consultant | add role desc | 175 | 0 | 0 | 0
TCO | Technical Consultant (Offshore) | add role desc | 115 | 0 | 0 | 0
QAE | Quality Assurance Engineer | add role desc | 115 | 0 | 0 | 0

## notes
stage | assumptions
initiate | > Skipping workshop sessions increases the risk that implementation planning and execution will misalign with the organizations most important business objective.
define
design
execute
transition
close

## ITSM_2
capability | task | task_details | role | hours | standard | pro | pro_plus | enterprise
Incident | Incident | Configure Incident Management as defined during workshops, limited to: > Using the OOTB predefined process and flow of the ServiceNow Incident Management application and modules > Using the OOTB predefined interoperability and flow of the ServiceNow Incident Management application, interacting with change, problem, knowledge, service level management and portal > Updating the Incident Table - up to ten (10) custom fields, up to two (2) business rule, up to two (2) UI actions, up to two (2) client scripts - to support a minimal change to the incident interface and workflow > Configure list view of the incident form > Configuration of the OOTB related lists (parent / child), providing visibility to OOTB related lists. | TC | 24 | Y | Y | Y | Y
Change | Change | Configure Change Management as defined during workshops, limited to: > Using the OOTB predefined process and flow of the ServiceNow Change Management application and modules > Using the OOTB predefined interoperability and flow of the ServiceNow Change Management application, interacting with problem, incident, knowledge, service level management and portal > Updating the Change Table - up to ten (10) custom fields, up to two (2) business rule, up to two (2) UI actions, up to two (2) client scripts - to support a minimal change to the change interface and workflows for Normal, Emergency and Standard Changes > Configure list view of the change form > Configuration of the OOTB related lists (parent / child), providing visibility to OOTB related lists. | TC | 24 | Y | Y | Y | Y
Release | Release |  | TC | 4 | Y | Y | Y | Y
Problem | Problem | Configure Problem Management as defined during workshops, limited to: > Using the OOTB predefined process and flow of the ServiceNow Problem Management application and modules > Using the OOTB predefined interoperability and flow of the ServiceNow Problem Management application, interacting with change, incident, knowledge, service level management and portal > Updating the Problem Table - up to five (5) custom fields, up to one (1) business rule, up to one (1) UI actions, up to one (1) client scripts - to support a minimal change to the problem interface and workflow > Configure list view of the problem form > Configuration of the OOTB related lists (parent / child), providing visibility to OOTB related lists. | TC | 12 | Y | Y | Y | Y
Request (Low) | Service Catalog Item / Request Process Configuration - Low Complexity | Create up to ten (10) Low Complexity Unique Catalog Items with corresponding workflows for Request Management. Low Complexity Catalog items contain up to five (5) variables, do not have dynamic menus or dependent values, do not have more than 1 approval task, do not have scripted Approvals, up to two (2) UI Policies or Client Scripts and do not explicitly necessitate their own unique workflow. Low Complexity Catalog Items typically have less than 5 total activities as part of their workflow, including one (1) task to fulfill the request. | TC | 40 | Y | Y | Y | Y
Request (Moderate) | Service Catalog Item / Request Process Configuration - Moderate Complexity | Create up to five (5) moderate complexity unique catalog items with corresponding workflows for Request Management. moderate complexity catalog Items contain up to fifteen (15) variables, have dynamic data-driven menus or dependent values, have up to three (3) workflow approval steps or require scripted approvals, and up to five (5) UI policies or client scripts. Moderate complexity catalog items typically require their own workflow, however still may share workflows depending on the use case. Moderate complexity catalog Items typically have less than 10 total activities as part of their workflow, including up to six (6) tasks to fulfill the request. | TC | 40 | Y | Y | Y | Y
Request (High) | Service Catalog Item / Request Process Configuration - High Complexity | Create up to one (1) High Complexity Unique Catalog Items with corresponding workflows for Request Management. High Complexity Catalog Items contain up to twenty-five (25) variables, have dynamic data-driven menus or dependent values, have up to five (5) Approval Steps or require scripted Approvals, and up to ten (10) UI Policies or Client Scripts. High Complexity Catalog Items require their own workflow and can have up to twenty (20) total activities, including up to ten (10) tasks as part of their workflow with multiple logic paths, to fulfill the request. | TC | 24 | Y | Y | Y | Y
Asset | Asset |  | TC | 4 | Y | Y | Y | Y
Cost | Cost |  | TC | 4 | Y | Y | Y | Y
Walk-Up Experience | Walk-Up Experience | task details | TC | 4 | Y | Y | Y | Y
Universal Request | Universal Request | task details | TC | 4 | Y | Y | Y | Y
Digital Portfolio Management | Digital Portfolio Management | task details | TC | 4 | Y | Y | Y | Y
App Engine Starter 25 | App Engine Starter 26 | task details | TC | 4 | Y | Y | Y | Y
Continual Improvement | Continual Improvement | task details | TC | 4 | N | Y | Y | Y
DevOps Change Velocity | DevOps Change Velocity | task details | TC | 4 | N | Y | Y | Y
Vendor Manager Workspace | Vendor Manager Workspace | task details | TC | 4 | N | Y | Y | Y
Financial Modelling | Financial Modelling | task details | TC | 4 | N | Y | Y | Y
Mobile Publishing | Mobile Publishing | task details | TC | 4 | N | Y | Y | Y
Predictive Intelligence | Predictive Intelligence | task details | TC | 4 | N | Y | Y | Y
Virtual Agent | Virtual Agent | task details | TC | 4 | N | Y | Y | Y
PA for ITSM | PA for ITSM | task details | TC | 4 | N | Y | Y | Y
Universal Request Pro | Universal Request Pro | task details | TC | 4 | N | Y | Y | Y
App Engine Starter 50 | App Engine Starter 51 | task details | TC | 4 | N | Y | Y | Y
DevOps Config | DevOps Config | task details | TC | 4 | N | Y | Y | Y
Virtual Agent Optimize | Virtual Agent Optimize | task details | TC | 4 | N | N | Y | Y
Workforce Optimization | Workforce Optimization | task details | TC | 4 | N | N | N | Y
Process Optimization | Process Optimization | task details | TC | 4 | N | N | N | Y